## W01
Documents managerment aplication
Group | <Group 6>
Week | <09/05/2022-15/05/2022>
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
| Choose project | Completed | Slot 1
| Deviding document for each member | Completed | Slot 1
| Working with SRS: - I-Overview/1.Intrdution; 2.System function(a,b,c) | Completed
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
| Analyze user requirement | Minh | Phân loại người dùng ứng dụng và chức năng của từng loại người dùng
| Design Context Diagram | Minh | Đã xong
| Write project's description | Nhân | Đã xong
| Design Screen Flow | Minh, Hiếu | Đã xong
| Write Screen Details | Nhân | Đã xong
| Write User Authorization | Nhân | Đã xong
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
| Fix Context Diagram | Completed
Pending
Pending
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
| Find WEB Skeleton | 16/05/2022
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
Note on C5: Author: Pending: just planned, have not started implementing yet In Progress: planned and doing, but have not completed yet Completed: planned and completed
Note on C20: Author: Pending: issue occurred, no solution yet In Progress: occurred and handling issue Completed: occurred and handled issue

## W02
Documents managerment aplication
Group | <Group 6>
Week | <16/05/2022-22/05/2022>
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
| Working with Product Backlog: - Write about 50 functions | Completed
| Working with SRS: - Fix Tash 2.System Functions(b, c) | Completed | Slot 4
In Progress
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
| Fix task b.Screen detail | Nhân
| Fix task c.User Authorization | Nhân
| Write Product Backlog | Huy | Function Name, Feature, Complexity (Simple)
| Draw ERD in paper | Whole team
| Design Wireframe | Trung
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
| Not enough functions | Completed | Working with Product Backlog (Added)
Pending
Pending
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
| Devide function for interation 1,2,3 |  | File Product Backlog
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
Note on C5: Author: Pending: just planned, have not started implementing yet In Progress: planned and doing, but have not completed yet Completed: planned and completed
Note on C21: Author: Pending: issue occurred, no solution yet In Progress: occurred and handling issue Completed: occurred and handled issue

## W03
Documents managerment aplication
Group | <Group 6>
Week | <23/05/2022-29/05/2022>
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
| Working with file SRS: + I. Overview/3.Common requirement + II. Functional Requirements | In Progress
| Working with file Design: + II. Code Designs/a. Draw class diagram | In Progress
| Prepare GitHub, GitLab | In Progress
In Progress
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
| Fix ERD | In Progress
Pending
Pending
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Prepare code packages
2 | Prepare Design document
3 | Complete each person's task in iteration 1
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
Note on C5: Author: Pending: just planned, have not started implementing yet In Progress: planned and doing, but have not completed yet Completed: planned and completed
Note on C18: Author: Pending: issue occurred, no solution yet In Progress: occurred and handling issue Completed: occurred and handled issue

## W04
Documents managerment aplication
Group | <Group 6>
Week | <30/05/2022-05/06/2022>
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
Completed
In Progress
In Progress
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
Minh
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
Pending
Pending
Pending
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
Note on C5: Author: Pending: just planned, have not started implementing yet In Progress: planned and doing, but have not completed yet Completed: planned and completed
Note on C17: Author: Pending: issue occurred, no solution yet In Progress: occurred and handling issue Completed: occurred and handled issue

## W05
Documents managerment aplication
Group | <Group 6>
Week | <09/05/2022-15/05/2022>
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
Completed
In Progress
In Progress
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
Minh
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
Pending
Pending
Pending
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
Note on C5: Author: Pending: just planned, have not started implementing yet In Progress: planned and doing, but have not completed yet Completed: planned and completed
Note on C17: Author: Pending: issue occurred, no solution yet In Progress: occurred and handling issue Completed: occurred and handled issue